## tasklist
Week	Start Date	End Date	Focus / Theme	Task Description	Primary Skill	Time Allocation (Est.)	Tools / Resources	Status
Week 1	2025-07-14	2025-07-20	Foundations: Mastering the Conversation	Task 1.1 (Weekdays): Read/watch tutorials on what LLMs, Transformers, and Tokens are. Understand the core concepts. / Task 1.2 (Weekdays): Learn the key differences between Zero-shot, One-shot, and Few-shot prompting. / Task 1.3 (Weekend): Use a web UI (Gemini, ChatGPT) to perform 10 different tasks. For each, document your initial prompt and 2 improved versions, noting why the changes worked. / Task 1.4 (Weekend): Start a 'Project Ideas' document and list 15+ commands you want your future AI assistant to handle.	Prompt Engineering	~14 Hours	Gemini/ChatGPT Web UI, Notion/Google Docs	Not Started
Week 2	2025-07-21	2025-07-27	The Engineer's Toolkit: Python & Hugging Face	Task 2.1 (Weekdays): Set up your Python environment with `venv` and install the `transformers` and `torch` libraries. / Task 2.2 (Weekdays): Write a Python script to use the Hugging Face `pipeline()` for text-generation and summarization. / Task 2.3 (Weekend): Experiment with at least 3 different models from the Hub within your pipeline script. Compare their outputs. / Task 2.4 (Weekend): Write a script that takes a hardcoded text command and uses a pipeline to execute a relevant task (e.g., sentiment analysis on a sentence).	Python for AI	~14 Hours	VS Code, Python 3.10+, Hugging Face Hub	Not Started
Week 3	2025-07-28	2025-08-03	How LLMs Learn: Datasets & Fine-Tuning Theory	Task 3.1 (Weekdays): Study the concepts of Pre-training vs. Fine-tuning. Understand what an instruction dataset is. / Task 3.2 (Weekdays): Browse instruction datasets on the Hugging Face Hub (e.g., databricks-dolly-15k, open-platypus). / Task 3.3 (Weekend): Write a Python script using the `datasets` library to load, inspect, and print 10-15 examples from a chosen instruction dataset. / Task 3.4 (Weekend): Take 10 commands from your 'Project Ideas' doc and manually format them into a JSON file following the instruction dataset structure (e.g., `{'instruction': '...', 'input': '...', 'output': '...'}`).	Data Handling	~14 Hours	VS Code, Hugging Face Datasets Library	Not Started
Week 4	2025-08-04	2025-08-10	Hands-On: Your First Fine-Tune	Task 4.1 (Weekdays): Read about Parameter-Efficient Fine-Tuning (PEFT), specifically the concepts of LoRA and QloRA. / Task 4.2 (Weekdays): Set up a Google Colab account and get familiar with its interface for using free GPUs. / Task 4.3 (Weekend): Find and complete a full tutorial notebook for fine-tuning a small model (e.g., OPT-350m or GPT-2) using QLoRA and the Hugging Face `Trainer` API. / Task 4.4 (Weekend): After fine-tuning, test your model with 5 new prompts and compare its performance to the base model.	Fine-Tuning	~14 Hours	Google Colab, Hugging Face `Trainer` & `peft`	Not Started
Week 5	2025-08-11	2025-08-17	Assistant's Brain: Advanced Prompting & Logic	Task 5.1 (Weekdays): Learn the theory behind advanced prompting techniques like Chain-of-Thought (CoT) and ReAct (Reason + Act). / Task 5.2 (Weekdays): Design the logic for your assistant. How does it get a command and decide what to do? / Task 5.3 (Weekend): Write a Python script that takes a complex command (e.g., "Find the top 3 Python libraries for web scraping and save them to a file.") and uses an LLM (via API) with a ReAct prompt to generate a step-by-step plan in JSON format.	System Design	~14 Hours	VS Code, OpenAI/Gemini API	Not Started
Week 6	2025-08-18	2025-08-24	Assistant's Senses: Voice & OS Control	Task 6.1 (Weekdays): Write a standalone Python script using the `SpeechRecognition` library that listens to your microphone and transcribes your speech to text in the console. / Task 6.2 (Weekdays): Write a separate script with functions to control your OS using the `subprocess` (for terminal commands) and `pyautogui` (for GUI automation) libraries. / Task 6.3 (Weekend): Create 3-4 simple OS control functions (e.g., `open_browser()`, `type_text('hello world')`, `press_enter()`). Test them thoroughly.	Automation & I/O	~14 Hours	VS Code, `SpeechRecognition`, `pyautogui`, `subprocess` libraries	Not Started
Week 7	2025-08-25	2025-08-31	Capstone Project v0.1: Integration	Task 7.1 (Weekdays): Plan the architecture of your final application. How will the 'Ears', 'Brain', and 'Hands' scripts communicate? / Task 7.2 (Weekend): Create the main `assistant.py` script. Implement a main loop that: 1. Listens for your voice command. 2. Sends the command to the 'Brain' to get a simple action. 3. Calls the correct OS control function from your 'Hands' script. / Task 7.3 (Weekend): Successfully integrate and test 2-3 simple commands end-to-end (e.g., "Hey assistant, open notepad.").	Integration	~14 Hours	All previous tools and scripts	Not Started
Week 8	2025-09-01	2025-09-07	Capstone Project v0.2: Refinement & Expansion	Task 8.1 (Weekdays): Implement more robust error handling. What happens if a voice command is not understood or an action fails? / Task 8.2 (Weekdays): Start a GitHub repository for your project, commit your code, and write a simple README.md file explaining your project. / Task 8.3 (Weekend): Add 3-5 more complex commands to your assistant. This might involve chaining multiple actions together. / Task 8.4 (Weekend): Review your entire journey, identify areas you want to learn more about, and plan your 'next steps' after this initial 8-week sprint.	Project Development	~14 Hours	GitHub, All previous tools	Not Started